## Slide 1
TEMPO Mission Project
July 23, 2013
Project Manager: Alan Little

## Slide 2: TEMPO Mission Project
TEMPO instrument selected under EVI-1
  AO solicited Science, Instrument, Operations, and associated project management, systems engineering, and safety and mission assurance
NASA responsible for getting TEMPO Instrument on orbit
  NASA Earth Science Division directed NASA LaRC to implement a flight project for the TEMPO satellite host

## Slide 3: TEMPO Organization
ESSP PO
Coordination of Mission activities
TEMPO
PI: Kelly Chance
Deputy PI: Xiong Liu
Program Administrator: Joseph Webber
Investigation Advisory Panel
Mission Management
Mission Project Manager: Alan Little
Deputy Project Manager/Resources: Don Shick
Instrument
Instrument PM: W. Pennington
Instrument DPM/COR: Craig Jones
CE: Dave Rosenbaum
Project Scientist: David Flittner
Systems Engineering
Mission Systems Engineer: TBN
Safety & Mission Assurance
SMA Manager: Jose Caraballo
Science Team
Mission Operations
Lead: TBN
Science Advisory Panel
Ground
System
Lead: TBN
Host Satellite
Lead: TBN
Management Support
Schedule Lead: Ken Parkinson
Configuration Manager: Kennedy Delgado
Resources: Linda Moore
Risk Manager: Craig Hutchinson
I&T
Lead: TBN
Instrument Project
Mission Project
Color code

## Slide 4: Concept of Operations

## Slide 5: What is HoPS?
HoPS: Hosted Payload Solutions
  Indefinite Delivery, Indefinite Quantity contract with “lanes” for LEO and GEO hosted payloads
  Implemented by USAF Space and Missile Systems Center (SMC)
  Fixed price contracts for Hosting
  RFP for Air Force contract will be released in Q4 FY13
NASA/SMC collaboration
  NASA is implementing a Memorandum of Agreement with SMC for collaboration on the HoPS contract
    NASA is supporting the RFP development and proposal evaluation

## Slide 6: TEMPO Accommodation Studies
TEMPO accommodation studies solicited through HoPS contract
  Solicitation included with HoPS RFP
  Up to four six-month studies to evaluate
    Accommodation of TEMPO instrument on GEO host satellites
      Address contamination, jitter
      Initial draft interface control document
    Identify launch opportunities that potentially meet TEMPO requirements
Coordinating with other NASA hosted payloads
  Laser Communications Relay Demonstration (LCRD)
  Global-scale Observations of the Limb and Disk (GOLD)

## Slide 7: TEMPO Mission Overview Schedule

## Slide 8: TEMPO Accommodation Mission Schedule Drivers
Primary Mission Schedule Drivers (details for each follow)
  1) Procurement of Host 2) Need for Early Design of Interfaces 3) Spacecraft Host Availability

## Slide 9: TEMPO Accommodation Mission Schedule Drivers
Primary Mission Schedule Drivers
  1) Procurement of Host
  2) Need for Early Design of Interfaces
  3) Spacecraft Host Availability
Procurement of Host
  Assuming utilization of HoPS (Air Force Hosted Payloads Solution office) IDIQ for procurement of Host
  HoPS IDIQ SOW planning/work to start after SRR (~Oct)
  Draft IDIQ SOW for Host is submitted to HoPS ~April 2014. Final release by HoPS ~October 2014. Host Contract award March 2015 with Host ATP May 2015.
  Can move right without affecting spacecraft timeline (no more than spacecraft ATP -2 months) but with potential increased risk to instrument/spacecraft interface design.

## Slide 10: TEMPO Accommodation Mission Schedule Drivers
Instrument
Primary Mission Schedule Drivers
  1) Procurement of Host
  2) Need for Early Design of Interfaces
  3) Spacecraft Host Availability
Interfaces Designed Early
  Current Schedule:
    Instrument PDR ~10/2014. CDR ~10/2015. Instrument complete ~5/2017.
    Host contract award ~3/2015. Spacecraft award notionally mid-2016 for 11/2018 launch.
  Original instrument assumption included spacecraft selection by instrument PDR or as early as possible after PDR.
  Time period between Instrument PDR & Host award poses risk to instrument-to-spacecraft interface.
  Work currently underway to identify interface bounding parameters and specific risks associated with later spacecraft ATP. Early TEMPO Host Accommodation studies will provide additional input into risk assessment.

## Slide 11: TEMPO Accommodation Mission Schedule Drivers
Primary Mission Schedule Drivers
  1) Procurement of Host
  2) Need for Early Design of Interfaces
  3) Spacecraft Host Availability
Spacecraft Host Availability
  Assuming a ~30 month spacecraft development cycle with payload need/instrument delivery 12 months prior to launch. Assuming earliest possible launch for planning purposes.
  Initial 18 months of spacecraft development cycle occur prior to instrument delivery, driving spacecraft ATP to ~6/2016.

## Slide 12: Key Dates
Key dates
  Spacecraft vendor known: between 5/15 and 6/16
  Spacecraft location known: ~5/15
  Spacecraft integration begins: 11/17
  Earliest launch: 11/18

## Slide 13
Backup